## EQMS Web Bug Report
Bug Report
Project Name: EQMS
Test Id | Test Module | Test Page | Issue Description | Test Data Set | Bug Priority | Status | Assigned By | Assigned To | Start Date | End Date | Total Time | Remarks | Manager Review
EQMS_01 | EQMS_WEB | Raise Change Control Page | 'Product' and 'Nature of Change' should also be kept as a mandatory fields | _ | High | Close | Rafi Azwad | Arman Hossain | 06.03.24 | 06.03.24 |  | Moving to the next page without selecting the mandatory field 'Nature of Change'(retest)
EQMS_02 | EQMS_WEB | Raise Change Control Page | Data is not saved as a draft without selecting the 'Product name' | _ | Medium | Close | Rafi Azwad | Arman Hossain | 29.02.24 | 29.02.24
EQMS_03 | EQMS_WEB | All Page | Data(submitted) should not be edited while search and filter the Complain List | _ | High | Deferred | Rafi Azwad | Arman Hossain |  |  |  | Not necessary
EQMS_04 | EQMS_WEB | Review of Proposed Change Page | Review of Proposed Change's submitted data doesn't come to 'Impact Assessment' | _ | Critical | Close | Rafi Azwad | Arman Hossain | 29.02.24 | 29.02.24
EQMS_05 | EQMS_WEB | Review of Proposed Change Page | Shows "CC Record Number" in Review of Proposed Change Page while selecting status as 'Reject-Cancelled' | _ | High | Close | Rafi Azwad | Arman Hossain | 29.02.24 | 29.02.24
EQMS_06 | EQMS_WEB | Change Plan Functional Approval Page | Missing "Review Status" in Change Plan Functional Approval List | _ | High | Close | Rafi Azwad | Arman Hossain | 29.02.24 | 29.02.24
EQMS_07 | EQMS_WEB | Change Plan Functional Approval Page | In "Change Plan" shows CC Record No: "came from: Change Plan Approval" while selecting status as 'Revise CC Plan'. But it came from 'Change Plan Functional Approval Page' | _ | High | Close | Rafi Azwad | Arman Hossain | 29.02.24 | 29.02.24
EQMS_08 | EQMS_WEB | Change Plan Approval Page | Missing "Review Status" in Change Plan Approval List | _ | High | Close | Rafi Azwad | Arman Hossain | 29.02.24 | 29.02.24
EQMS_09 | EQMS_WEB | Change Plan Approval Page | Moving to the next page(Implimentation) when selecting status as 'Rejected/Revised CC Plan/Revised Impact Assessment' | _ | Critical | Close | Rafi Azwad | Arman Hossain | 03.03.24 | 03.03.24
EQMS_10 | EQMS_WEB | Implementation Page | Does't show who implemented [Quality Final Review (Draft)] | _ | High | Close | Rafi Azwad | Arman Hossain | 29.02.24 | 29.02.24
EQMS_11 | EQMS_WEB | Quality Final Review Page | Missing "Review Status" in Quality Final Review List | _ | High | Close | Rafi Azwad | Arman Hossain | 29.02.24 | 29.02.24
EQMS_12 | EQMS_WEB | Change Plan Approval Page | When selecting status as "Rejected" data doesn't save in Approval Status as Rejected in Change Plan Approval List | _ | High | Close | Rafi Azwad | Arman Hossain | 06.03.24 | 06.03.24
EQMS_13 | EQMS_WEB | Dashboard Page | Review of Proposed Change Page's 'Pending count' doesn't match | _ | High | Close | Rafi Azwad | Arman Hossain | 06.03.24 | 06.03.24
EQMS_14 | EQMS_WEB | Dashboard Page | Change Plan page's 'Draft and Submitted count' doesn't match | _ | High | Close | Rafi Azwad | Arman Hossain | 06.03.24 | 06.03.24
EQMS_15 | EQMS_WEB | Dashboard Page | Change Plan Functional Approval's 'Pending count' doesn't match(when draft) | _ | High | Close | Rafi Azwad | Arman Hossain | 06.03.24 | 06.03.24
EQMS_16 | EQMS_WEB | Dashboard Page | Implementation QA Review's 'Pending, Draft and Submitted count' doesn't match | _ | High | Close | Rafi Azwad | Arman Hossain | 06.03.24 | 06.03.24
EQMS_17 | EQMS_WEB | Dashboard Page | After clicking on 'Total' of 'Rise Change Control' moves to another page | _ | High | Close | Rafi Azwad | Arman Hossain | 06.03.24 | 06.03.24
EQMS_18 | EQMS_WEB | Change Control Status Page | 'Draft and Submitted' don't work in Status while filtering | _ | High | Close | Rafi Azwad | Arman Hossain | 06.03.24 | 06.03.24
EQMS_19 | EQMS_WEB | Change Plan Page | When Status is selected as 'Revise Impact Assessment' in 'Change Plan Functional Approval and Change Plan Approval Page', it doesn't show which page it came from in 'CC Record No'. | _ | High | Close | Rafi Azwad | Arman Hossain | 07.03.24 | 07.03.24
EQMS_20 | EQMS_WEB | All Page | 'Print' option doesn't work | _ | High | Close | Rafi Azwad | Arman Hossain | 10.03.24 | 10.03.24
EQMS_21 | EQMS_WEB | Change Control Proposal Page | Change Control Raise's data has been submitted but shows as 'Draft' | _ | High | Close | Rafi Azwad | Arman Hossain | 10.03.24 | 10.03.24